## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Plan
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Student Insights : A Power BI Approach
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE | data profiling , analysing and then visualizing to gain insights
PROJECT START DATE | 2025-07-28
PROJECT END DATE | 2025-08-03
OVERALL PROGRESS | COMPLETED
INTERN ID | IP-7051
Student Name | Aryan Sunil Bendre
SL NO | TASK NAME | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Understanding business problem | 2025-07-28 | 2025-07-28 | 1 | COMPLETED
| 1.2 Understanding data | 2025-07-28 | 2025-07-28 | 1 | COMPLETED
| 1.3 Create a project charter | 2025-07-28 | 2025-07-28 | 1 | COMPLETED
| 1.4 Creating SRS document | 2025-07-28 | 2025-07-28 | 1 | COMPLETED
2 Planning
| 2.1 Data Collection and Preparation | 2025-07-29 | 2025-07-29 | 1 | COMPLETED
| 2.2 Initial Data Exploration | 2025-07-29 | 2025-07-29 | 1 | COMPLETED
| 2.3 Preliminary Visualizations | 2025-07-30 | 2025-07-30 | 1 | COMPLETED
| 2.4 Initial Findings and Goal Setting | 2025-07-30 | 2025-07-30 | 1 | COMPLETED
| 2.5 Advanced Data Analysis | 2025-07-31 | 2025-07-31 | 1 | COMPLETED
| 2.6 Enhanced visualization and Dashboard | 2025-07-31 | 2025-07-31 | 1 | COMPLETED
| 2.7 Validation and Testing | 2025-07-30 | 2025-07-30 | 1 | COMPLETED
| 2.8 Final presentation and Documentation | 2025-07-30 | 2025-07-30 | 1 | COMPLETED
| 2.9 Project Review and closure | 2025-07-30 | 2025-07-30 | 1 | COMPLETED
3 Execution
| 3.1 Data Collection | 2025-07-31 | 2025-07-31 | 1 | COMPLETED
Import the dataset into Power BI.
Review the data to understand its structure and format.
| 3.2 Data Cleaning | 2025-07-31 | 2025-07-31 | 1 | COMPLETED
| 3.2.1 Data tranforming | 2025-07-31 | 2025-07-31 | 1 | COMPLETED
Handle missing, duplicate entries, and inconsistent data formats
Normalize and structure the data for analysis.
| 3.3 Initial data Exploration | 2025-07-31 | 2025-07-31 | 1 | COMPLETED
Calculate basic descriptive statistics (mean, median, mode, standard deviation).
Profile key variables to understand their distribution.
| 3.4 Corelation Analysis | 2025-08-01 | 2025-08-01 | 1 | COMPLETED
Examine relationships between key variables (e.g., family income and GPA)
| 3.5 Preliminary Visualizations | 2025-08-01 | 2025-08-01 | 1 | COMPLETED
Create distribution charts (histograms, bar charts) for key variables.
Develop box plots to identify outliers.
| 3.6 Advanced Data analysis | 2025-08-01 | 2025-08-01 | 1 | COMPLETED
Begin clustering analysis to group similar students based on key metrics
Develop and test initial predictive models for student success and expected salary.
| 3.7 Enhaced Visualizations | 2025-08-02 | 2025-08-02 | 1 | COMPLETED
Enhance Power BI dashboard with interactive elements (filters, drill-downs).
| 3.8 Validation And Testing | 2025-08-02 | 2025-08-02 | 1 | COMPLETED
Validate predictive models and verify outliers.
| 3.9 Documentation | 2025-08-02 | 2025-08-02 | 1 | COMPLETED
Document data analysis processes and methodologies used.
| 4. Closure | 2025-08-03 | 2025-08-03 | 1 | COMPLETED