## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Student Insights : A Power BI Approach |  | Intern Id: | IP-7051 | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1.2 |  | Last Updated date: | 2025-07-30 | Project Team Lead: | Aryan Sunil Bendre |  |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Data Inaccuracy | Findings and visualizations would be incorrect, leading to flawed business decisions and a loss of trust in the analysis. | Prioritize the use of the Cleaned_All Events Data.csv file and clearly state that all findings are based on the data provided | Project Manager | Critical | 1 | Closed | Risk
2 | Risk | Misinterpretation of Findings | Stakeholders might mistake correlation for causation (e.g., assuming GPA causes higher salary), leading to misplaced focus. | Use precise language in reports ("correlates with," "tends to have") and advise that causation requires deeper statistical analysis. | Project Manager | High | 2 | Closed | Assumption
3 | Assumption | The "Cleaned" data file was reliable. | The entire analysis would be built on a faulty foundation, rendering all results and insights invalid. | Perform spot-checks and data profiling to validate the "cleaned" data. Document the dependency on this file in all reports. | Project Manager | Moderate | 3 | Closed | Issue
4 | Assumption | The user had necessary Power BI permissions. | The user would be unable to implement admin-level solutions (like enabling maps), causing project delays and frustration. | State permission requirements upfront as a prerequisite for specific tasks and clearly note when an administrator is needed. | Project Manager | Moderate | 3 | Closed | Dependency
5 | Issue | Incorrect data type for the salary column. | All salary-based calculations failed, and the Power BI visual was broken, preventing any reporting on this key metric | Provided step-by-step instructions to change the column's data type from Text to Decimal Number in Power Query. | Project Manager | Low | 5 | Closed
6 | Issue | Disabled map visuals at the admin level | The user was blocked from creating any geographic visualizations, limiting their ability to analyze location-based data. | Provided instructions for a Power BI Administrator to enable the visuals in the Admin Portal's Tenant Settings. | Project Manager | Low | 5 | Closed | Open
7 | Dependency | Availability of Source Data: The project is entirely dependent on the user providing a valid and accessible Cleaned_All Events Data.csv file. | The project cannot begin; no analysis is possible. |  | Project Manager | Moderate | 4 | Closed | Closed
8 | Dependency | Correctly Configured Power BI Environment: The creation of certain visuals (e.g., Maps) is dependent on the proper setup in the user's Power BI Admin Portal. | Key visualizations requested by the user cannot be created, leading to an incomplete or less insightful report. |  | Project Manager | Moderate | 4 | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24